## Woburn 23 March 2024
Date | When | Activity | Who | Committee responsibility | Status
|  | Book Venue | Peter |  | Done | 2024-03-23
|  | Arrange St John Ambulance( 6 months in advance) | Sian | Peter
2023-10-07 | 6 months before | Circulate proforma (next tab) (details and timeline for concert) to committee and publicity team | Beverley
|  | Check insurance arrangements for concert and venue |  | Chair to check insurance
|  | Arrange provision of organ and speakers to go behind choir | David |  | N/A
|  | Arrange equipment (speakers, amplifier, microphone) to relay organ behind choir | David/Stuart |  | N/A
Arrange soloists - Peter needs to know fees agreed
Arrange provision of instruments
2024-03-02 | 3 weeks before | Arrange loan of chairs from Linslade Academy | Peter Snelling
|  | Book hire van and arrange driver | Peter Skelton
|  | Invite President to concert | Chair
|  | Give choir numbers/voice parts to Sian and Yvonne for voice parts in programme | Amanda/Sian/ Yvonne
|  | Liaise with Ian about how choir seating will be arranged. | Sian | Ian
|  | Find the usual seating plan for the venue. | Sian
|  | Ask choir if anyone has special seating (usually medical) needs. | Sian
|  | Make approximate seating plan, matching seats to voice part numbers. | Sian
|  | Draw up audience seating plan; prepare seat labels | Peter Snelling | Audience seating plan already established for selling tickets; labels reused from previous concerts
|  | Make arrangements for orchestra tea | Sian
|  | Recruit front of house team, programme and ticket sales, ushers. Agree numbers (6), start time, responsibilities, admission time for audience. | Non-singing members | Peter Snelling,
|  | Recruit volunteers to set up church (seating, lighting, audience, etc) |  | Peter Snelling
|  | Recruit volunteers to dismantle seating, lighting, etc. after concert. |  | Peter Snelling
|  | Contact key holder and arrange access at church for 9.30 on Saturday | Peter Snelling
2024-03-16 | 1 week before | Share choir seating plan with Ian as he may suggest changes. | Sian
2021-03-24 | Wednesday before concert | Collect conductor's podium from AG Village Hall | Sian
2024-03-22 | Friday before concert | Supervise collection of hire van,collect plastic chairs | Peter Skelton
|  | Collect 150 plastic chairs from Linslade Academy | Peter Skelton
|  | Collect staging, red chairs & lighting from storage | Peter Skelton
|  | Drive van to suitable overnight location. | Peter Skelton
|  | Buy wine and flowers for soloists (find out budget) | Sian
|  | Recruit volunteers to present gifts to soloists | Sian
|  | Get music stands for orchestra | Ian
2024-03-23 | Concert Saturday | Collect key from key holder; find out about opening and closing church; switching lights on and off. | Peter 9.30
|  | Drive van to Woburn church | Peter Skelton
|  | Supervise unloading of van and positioning in logical sequence |  | access for 9.30
|  | Supervise setting up of church including additional audience seating, and labels | Peter | Peter Snelling
Erect staging, choir seating, labels, placing of podium
|  | Erect lighting as usual plus PA testing (as required) | Stuart Freake
Deliver music stands to church
|  | Set up music stands for orchestra | Ian
Move piano to back of RH aisle
Remove modesty panel on front LH pew to allow more room for strings
|  | Put mobility ramp in place before concert |  | Jeremy
|  | Adjust choir seating plan if necessary. | Sian
|  | Put out voice part labels on choir seats | Sian
|  | Complete risk assessment (see last tab) | Chair
Ask front of house team to be in place by 18:45
Make sure someone on ticket desk
|  | Make sure volunteers have gifts to present to soloists | Siân
|  | Prepare words of introduction before the concert | Ian
| After concert | Supervise dismantling of stage,chairs & lighting, loading of van | Peter Skelton
|  | Restore church to usual state |  | Jeremy
|  | Bring mobility ramp inside |  | Jeremy
2024-03-24 | Sunday | Supervise return of staging, red chairs and lighting to storage | Peter Skelton
2024-03-25 | Monday | Return plastic chairs to Linslade Academy | Peter Skelton
|  | Return hire van | Peter Skelton
2022-04-06 | Wednesday | Return conductor's podium to AG village hall | Sian

## Marketing and publicity
Week commencing | Timing | Activity | Who? | Activity area
2022-03-26 | -104 weeks | Book venue | Peter | Venue
2023-10-21 | -22 weeks | Circulate proforma (details, incl soloists and timeline for concert) | Concert Secretary | Management | 2024-03-23
2023-11-04 | -20 or -18 weeks | Start poster and flyer design | David | Posters/flyers
2023-11-18 | -18 weeks | Liaise with Helen Richards about numbers of posters and flyers to be printed; more are needed for joint concerts (up to 10,000 for MK Chorale, MK Theatre, Danesborough). Usually 2,500 flyers. Need enough for Polymnia to distribute at their concerts. | David/Helen Richards | Posters/flyers
2023-11-18 | -18 weeks | Send posters and flyers to printer (allow one week) | David | Posters/flyers
2023-11-25 | -17 weeks | Book library displays | Helen Richards | Displays
2023-11-25 | -17 weeks | Prepare ticket files |  | Tickets
2023-11-25 | -17 weeks | Prepare and print booking form (ensure Eleanor's contact details are correct). Include use of data statement. Upload to website. | Jenny | Tickets
2023-12-16 | -14 weeks | Print tickets |  | Tickets
2023-12-23 | -13 weeks | Sort tickets |  | Tickets
2023-12-23 | -13 weeks | Flyers and posters available for distribution | Helen Richards | Posters/flyers
2023-12-30 | -12 weeks | Update adverts list, highlight advertisers that need renewal. Give rate cards to the advertising team (?/Dunstable; Beverley/Woburn; Jenny/Leighton Buzzard; ??/Woburn Sands) | Yvonne | Advertisements
2023-12-30 | -12 weeks | Tickets to box office (in readiness for Friends’ orders) |  | Tickets
2020-01-04 | -12 weeks | Draft press release to publicise concert and send for approval | ?/Ian | Press release
2024-01-06 | -11 weeks | Prepare and mail letter to Friends + booking form | Yvonne | Friends of DC
2024-01-06 | -11 weeks | Forward Friends letter to Jenny for letter/email to concert-goers | Yvonne | Tickets
2024-01-06 | -11 weeks | Liaise with contracts secretary for soloists biographies and photos | Yvonne/Beverley | Programme
2024-01-06 | -11 weeks | Liaise with Gina Johnson re: Polymnia advert in DC programme | Yvonne | Programme
2024-01-06 | -11 weeks | Contact Stuart Brown re: writing programme notes | Yvonne/David | Programme
2024-01-13 | -10 weeks | Draft letter to concert-goers based on Friends’ letter, flyer,press release | Jenny | Letter to concert-goers
2024-01-20 | -9 weeks | Finalise, print and send out leter to concert-goers (14 recipients) | Jenny | Letter to concert-goers
2024-01-20 | -9 weeks | Begin sending press release/adverts to local press and websites | Sian | Press release
2024-01-27 | -8 weeks | Send out Mailchimp version of letter to concert-goers to email recipients(120) | Jenny Harris/Jenni Ferrans | Email to concert-goers
2024-01-27 | -8 weeks | Box office opens | Eleanor & Gerry | Tickets
2024-01-27 | -8 weeks | Write programme notes and send to Ian | David & Stuart Brown | Programme
2024-02-10 | -6 weeks | Put up library displays and arrange delivery of posters and flyers to all Beds and North Bucks libraries and other relevant organisations | Helen Richards | Displays
2024-02-24 | -4 weeks | Start work on preparing programme | David | Programme
2024-02-24 | -4 weeks | Liaise with press over more details, photos and tickets |  | News release
2024-03-02 | -3 weeks | Provide ad artwork & advertisers to David | Yvonne/David | Advertisements/programme
2024-03-02 | -3 weeks | Soloist biographies and photos | Yvonne to David | Programme
2024-03-02 | -3 weeks | List of choir singers confirmed & given to Yvonne | Sian | Programme
2024-03-02 | -3 weeks | Give choir list, Friends list, adverts list + artwork, programme notes to David | Yvonne to David | Programme
2024-03-09 | -2 weeks | Obtain orchestra list | Yvonne/David | Programme
2024-03-16 | -1 week | Print programme | David | Programme
2024-03-23 | 0 week | Concert: Bach St John Passion
Note on C3: David Roberts: Ideally, if we are to be able to reintroduce annual flyers, the lead time for this could be up to 70 weeks. The first draft may be incomplete and then serves to identify what needs to be done, e.g. Book soloists, set ticket prices.

## Publicity pro-forma
Venue | Woburn Parish Church
Date | 2024-03-23
Time | 19:30
Programme in running order
Soloists (from choir)
Accompaniment (with names)
Hire instruments (with source)
Ticket prices | Band 1 (Reserved) | Band 2 (Reserved) | Band 3 (Unreserved) | Band 4 | Band 5
| 20 | 15 | 10
Concessions | £5 (under-18s)
Complimentary tickets | Ian Smith x 2
Tim Grant-Jones x 2
Soloists x2
Programme price | 1

## Seating chairs
| Total | 78 Woburn red chairs | 150 Linslade Academy chairs
Total audience seats
Number of chairs needed for audience seating
Total choir seats
Number of chairs needed for choir
Total orchestra seats | N/A | N/A
Number of chairs needed for orchestra | N/A | N/A
Total soloist seats | N/A | N/A
Number of chairs needs for soloists | N/A | N/A

## Risk Assessment
What is the hazard? | Who might be harmed and how? | What are we doing short-term? | What do we need to do medium term? | Action by whom? | Status (done/date)
Trips and falls | Choir members. | Ensure floor covering by pews securely fixed. | Review seating arrangements. | Saturday crew/Chair
|  | Members with mobility problems to sit at front of choir. |  | SR/Chair
|  | Remind choir members to take care. |  | Chair brief
Lighting poles falling over | Audience, choir members, orchestra members hit by falling light | Ensure lights securely set up. |  | SF/Chair
|  | Ensure lights not in any passage way. |  | SF/Chair
Faulty lighting/wiring causing electric shock. | Setting up crew, choir, orchestra, audience touching light | Setting up crew to take appropriate measures. | PAT testing. | SF | Recommendation is that PAT testing should be done every 12-24 months for moveable eqiupment
Medical Emergency | Audience, choir members, orchestra members | Arrange attendance of St John Ambulance |  | SR